## Users
user_id | username | password_hash | full_name | email | role | external_helpdesk_agent_id | is_active | created_at
USR-101 | mayur | e8024e73c6f4ea8a7da8ac227de1b7562e2d0962ebb8447dded804d80c67b52e | Mayur R | mayur@casco.com | AGENT | mayur123 | TRUE | 2026-01-10 09:00:00
USR-102 | lead_user | e8024e73c6f4ea8a7da8ac227de1b7562e2d0962ebb8447dded804d80c67b52e | Sarah Connor (Lead) | sarah@casco.com | LEAD | sarah456 | TRUE | 2026-01-10 09:00:00
USR-103 | admin_user | e8024e73c6f4ea8a7da8ac227de1b7562e2d0962ebb8447dded804d80c67b52e | System Admin | admin@casco.com | ADMIN | admin999 | TRUE | 2026-01-10 09:00:00

## Tickets
ticket_id | external_id | subject | description | priority | status | assigned_agent_id | assigned_agent_name | created_at | updated_at | last_sync_at | tags | is_stale
INC-10234 | INC-10234 | SMTP Outbound Email Timeout in Bottomline Engine | Users reporting email notifications fail when sending batch PO invoices. Connection times out after 30s. | High | In Progress | USR-101 | Mayur R | 2026-09-04 09:15:00 | 2026-09-04 15:00:00 | 2026-09-09 10:00:00 | SMTP,Bottomline,Production | FALSE
INC-10121 | INC-10121 | EDI 850 Purchase Order Parsing Failure in QAD | EDI inbound stream fails on vendor 850 files containing special characters in line items. | Critical | Pending | USR-101 | Mayur R | 2026-09-02 11:30:00 | 2026-09-03 14:20:00 | 2026-09-09 10:00:00 | EDI,QAD,Critical | TRUE
INC-10088 | INC-10088 | NiceLabel Barcode Printer Driver Crash on Shipping Line 2 | Thermal barcode printer disconnects during high volume shift prints. | Medium | Open | USR-101 | Mayur R | 2026-09-01 08:00:00 | 2026-09-01 08:00:00 | 2026-09-09 10:00:00 | NiceLabel,Hardware | TRUE

## Ticket_Updates
update_id | ticket_id | agent_id | agent_name | update_text | status_after | timestamp | next_action | follow_up_date
TUPD-001 | INC-10234 | USR-101 | Mayur R | Checked SMTP configuration on Bottomline server. Listener port 25 is active. | In Progress | 2026-09-04 10:30:00 | Run packet capture on port 25 | 2026-09-05
TUPD-002 | INC-10234 | USR-101 | Mayur R | Found connection timeout in firewall log between app server and mail relay. | In Progress | 2026-09-04 13:15:00 | Contact Infra team for firewall rule check | 2026-09-06
TUPD-003 | INC-10234 | USR-101 | Mayur R | Escalated issue to infrastructure network team. Awaiting firewall log review. | Pending | 2026-09-04 15:00:00 | Follow up with Infra lead | 2026-09-09

## Tasks
task_id | title | description | project | category | priority | status | assignee_id | assignee_name | start_date | due_date | completion_pct | created_at | updated_at | related_ticket_id
TASK-1001 | Upgrade NiceLabel Enterprise Server to v10.4 | Apply security patch and test template compatibility across production lines. | Infrastructure | Software Upgrade | High | In Progress | USR-101 | Mayur R | 2026-09-01 | 2026-09-08 | 60 | 2026-09-01 09:00:00 | 2026-09-07 16:00:00 | INC-10088
TASK-1002 | QAD Progress 4GL Database Index Optimization | Re-index customer order table to improve batch query execution speed. | Database Maintenance | Performance | Medium | Open | USR-101 | Mayur R | 2026-09-05 | 2026-09-12 | 20 | 2026-09-05 10:00:00 | 2026-09-05 10:00:00

## Task_Updates
update_id | task_id | agent_id | agent_name | update_text | status_after | completion_pct_after | timestamp
TKUPD-001 | TASK-1001 | USR-101 | Mayur R | Completed stage 1 backup of NiceLabel server configuration. | In Progress | 30 | 2026-09-02 11:00:00
TKUPD-002 | TASK-1001 | USR-101 | Mayur R | Staged v10.4 installer on QA environment and verified label rendering. | In Progress | 60 | 2026-09-07 16:00:00

## Documents
doc_id | title | category | description | version | uploaded_by_id | uploaded_by_name | uploaded_date | modified_date | file_path | tags | related_item_id
DOC-501 | SMTP Server Integration & Troubleshooting Guide | Troubleshooting | Step-by-step resolution for Bottomline SMTP connection timeouts and relay rules. | 2.1 | USR-102 | Sarah Connor | 2026-08-15 10:00:00 | 2026-08-15 10:00:00 | /uploads/smtp_guide.pdf | SMTP,Bottomline,Mail | INC-10234
DOC-502 | QAD Progress 4GL Interface Architecture Specification | Interfaces | Technical overview of QAD Progress 4GL database sockets and EDI translators. | 1.4 | USR-102 | Sarah Connor | 2026-07-20 14:00:00 | 2026-07-20 14:00:00 | /uploads/qad_interface.pdf | QAD,Progress 4GL,EDI | INC-10121

## Knowledge_Base
article_id | title | category | problem_summary | validation_checks | solution_steps | related_doc_ids | related_ticket_ids | created_at | updated_at
KB-201 | SMTP Connection & Email Delivery Troubleshooting | Troubleshooting | Emails fail to send from Bottomline or QAD system with connection timeout error. | ["1. Verify port 25/587 ping from application server.", "2. Check Bottomline Windows Service status.", "3. Inspect firewall outgoing logs.", "4. Validate relay IP whitelisting on Exchange/Office365."] | ["Step 1: Open PowerShell on app server and test `Test-NetConnection -ComputerName smtp.casco.com -Port 25`.", "Step 2: Restart 'Bottomline Output Server' service if socket hangs.", "Step 3: If firewall drops packets, submit emergency ticket to Network Operations."] | ["DOC-501"] | ["INC-10234"] | 2026-08-20 10:00:00 | 2026-08-20 10:00:00

## Audit_Log
audit_id | user_id | username | action | entity | entity_id | timestamp | result | details
AUD-001 | USR-101 | mayur | SYSTEM_INIT | System | SYS | 2026-09-09 10:00:00 | SUCCESS | Initial seed data loaded into Excel repository.

## Personal_Notes
note_id | user_id | title | content | updated_at